## Activities - Engineering
Activity ID | Activity Name | Phase | Cost Category | Period | Baseline Start | Baseline Finish | Forecast Start | Forecast Finish | Actual Start | Actual Finish | % Complete | Status | Variance (Days) | Root Cause | Impact | Budget Cost (AED) | Actual Cost (AED) | Forecast Cost (AED) | Planned Hours | Actual Hours | Planned Output | Actual Output | Output Unit | Productivity Index
ENG-01 | Site Survey & Soil Investigation | Engineering | Engineering & Design Fees | P1 | 2024-02-01 | 2024-02-10 | 2024-02-01 | 2024-02-09 | 2024-02-01 | 2024-02-09 | 100% | Completed | -1 | - | None | 20000 | 20000 | 20000
ENG-02 | Architectural Drawings - IFC | Engineering | Engineering & Design Fees | P1 | 2024-02-05 | 2024-02-25 | 2024-02-06 | 2024-03-02 | 2024-02-06 | 2024-03-02 | 100% | Delayed | 6 | Client review delays | Low | 35000 | 35000 | 35000
ENG-03 | Structural Design & Calculations | Engineering | Engineering & Design Fees | P2 | 2024-02-10 | 2024-03-01 | 2024-02-11 | 2024-03-04 | 2024-02-11 | 2024-03-04 | 100% | Delayed | 3 | Late input from geotech report | Medium | 40000 | 40000 | 40000
ENG-04 | MEP Coordination Drawings | Engineering | MEP Works | P2 | 2024-02-15 | 2024-03-10 | 2024-02-18 | 2024-03-15 | 2024-02-18 | 2024-03-15 | 100% | Delayed | 5 | Design clashes requiring rework | Medium | 190000 | 187500 | 190000
ENG-05 | Landscape & Civil Design | Engineering | Engineering & Design Fees | P1 | 2024-02-12 | 2024-02-28 | 2024-02-12 | 2024-02-28 | 2024-02-12 | 2024-02-28 | 100% | Completed | 0 | - | None | 15000 | 15000 | 15000
ENG-06 | Fire & Life Safety Design | Engineering | Engineering & Design Fees | P2 | 2024-03-01 | 2024-03-18 | 2024-03-01 | 2024-03-22 | 2024-03-01 | 2024-03-22 | 100% | Delayed | 4 | Code compliance revisions | Low | 25000 | 26500 | 26500
ENG-07 | Geotechnical Peer Review | Engineering | Engineering & Design Fees | P1 | 2024-02-08 | 2024-02-20 | 2024-02-08 | 2024-02-20 | 2024-02-08 | 2024-02-20 | 100% | Completed | 0 | - | None | 12000 | 12000 | 12000
ENG-08 | BIM Coordination Model - Final | Engineering | Engineering & Design Fees | P2 | 2024-03-05 | 2024-03-25 | 2024-03-05 | 2024-03-30 | 2024-03-05 | 2024-03-30 | 100% | Delayed | 5 | Additional clash detection rounds | Low | 28000 | 29500 | 29500

## Activities - Procurement
Activity ID | Activity Name | Phase | Cost Category | Period | Baseline Start | Baseline Finish | Forecast Start | Forecast Finish | Actual Start | Actual Finish | % Complete | Status | Variance (Days) | Root Cause | Impact | Budget Cost (AED) | Actual Cost (AED) | Forecast Cost (AED) | Planned Hours | Actual Hours | Planned Output | Actual Output | Output Unit | Productivity Index
PRC-01 | Rebar Procurement | Procurement | Material Procurement | P2 | 2024-02-20 | 2024-03-05 | 2024-02-20 | 2024-03-05 | 2024-02-20 | 2024-03-05 | 100% | Completed | 0 | - | None | 60000 | 60000 | 60000
PRC-02 | Ready-Mix Concrete Supplier Contract | Procurement | Material Procurement | P2 | 2024-02-25 | 2024-03-08 | 2024-02-28 | 2024-03-14 | 2024-02-28 | 2024-03-14 | 100% | Delayed | 6 | Supplier price renegotiation | Medium | 70000 | 68000 | 70000
PRC-03 | Structural Steel Procurement | Procurement | Material Procurement | P2 | 2024-03-01 | 2024-03-20 | 2024-03-05 | 2024-03-30 | 2024-03-05 | 2024-03-30 | 100% | Delayed | 10 | Mill lead-time longer than quoted | High | 100000 | 95000 | 98000
PRC-04 | MEP Equipment Long-Lead Items | Procurement | Material Procurement | P3 | 2024-03-05 | 2024-04-01 | 2024-03-10 | 2024-05-03 | 2024-03-10 |  | 70% | Delayed | 32 | Chiller delivery delayed by manufacturer | High | 80000 | 75000 | 77000
PRC-05 | Elevator & Lift Package | Procurement | Vertical Transportation | P2 | 2024-03-10 | 2024-04-10 | 2024-03-12 | 2024-04-20 | 2024-03-12 |  | 80% | Delayed | 10 | OEM factory backlog | Medium | 220000 | 180000 | 225000
PRC-06 | Facade & Glazing Package | Procurement | Facade & Glazing | P3 | 2024-03-20 | 2024-04-15 | 2024-03-25 | 2024-04-30 | 2024-03-25 |  | 50% | Delayed | 15 | Custom glass unit lead time | High | 260000 | 140000 | 270000
PRC-07 | Interior Finishes Materials Package | Procurement | Fit-Out & Finishes | P3 | 2024-04-05 | 2024-04-25 | 2024-04-08 | 2024-05-02 | 2024-04-08 |  | 60% | Delayed | 7 | Tile supplier backorder | Medium | 95000 | 58000 | 98000
PRC-08 | Landscaping Materials & Plants | Procurement | Landscaping & External Works | P4 | 2024-05-15 | 2024-05-30 | 2024-05-15 | 2024-05-30 |  |  | 0% | Not Started | 0 | - | None | 40000 | 0 | 40000

## Activities - Construction
Activity ID | Activity Name | Phase | Cost Category | Period | Baseline Start | Baseline Finish | Forecast Start | Forecast Finish | Actual Start | Actual Finish | % Complete | Status | Variance (Days) | Root Cause | Impact | Budget Cost (AED) | Actual Cost (AED) | Forecast Cost (AED) | Planned Hours | Actual Hours | Planned Output | Actual Output | Output Unit | Productivity Index
CON-01 | Excavation & Shoring | Construction | Civil Works | P2 | 2024-03-01 | 2024-03-15 | 2024-03-03 | 2024-03-20 | 2024-03-03 | 2024-03-20 | 100% | Delayed | 5 | Groundwater management | Medium | 80000 | 85000 | 88000 | 4200 | 4850 | 620 | 540 | m3 poured | 75.42%
CON-02 | Foundation & Raft Slab Pour | Construction | Civil Works | P2 | 2024-03-10 | 2024-03-28 | 2024-03-15 | 2024-04-05 | 2024-03-15 | 2024-04-05 | 100% | Delayed | 8 | Rebar procurement delay upstream | High | 120000 | 128000 | 132000 | 3100 | 3400 | 85 | 76 | tons fixed | 81.52%
CON-03 | Substructure Waterproofing | Construction | Civil Works | P3 | 2024-03-25 | 2024-04-05 | 2024-04-01 | 2024-04-28 | 2024-04-01 |  | 60% | Delayed | 23 | Follows foundation pour completion | Medium | 60000 | 62000 | 64000 | 1800 | 1650 | 40 | 34 | tons erected | 92.73%
CON-04 | Superstructure - Ground to L3 Columns | Construction | Civil Works | P3 | 2024-04-01 | 2024-04-25 | 2024-04-03 | 2024-05-02 | 2024-04-03 |  | 45% | Delayed | 7 | Concrete supplier renegotiation impact | High | 90000 | 95000 | 98000 | 2600 | 2900 | 310 | 275 | linear meters | 79.53%
CON-05 | Superstructure - Slab L1 | Construction | Civil Works | P3 | 2024-04-10 | 2024-04-30 | 2024-04-10 | 2024-05-05 |  |  | 15% | Delayed | 5 | Sequenced after column pours | Medium | 30000 | 32500 | 33000 | 1500 | 1400 | 210 | 205 | m2 completed | 104.6%
CON-06 | Site Mobilization & Hoarding | Construction | Equipment Idle Time | P1 | 2024-02-01 | 2024-02-07 | 2024-02-01 | 2024-02-07 | 2024-02-01 | 2024-02-07 | 100% | Completed | 0 | - | None | 25000 | 41200 | 46000 | 900 | 1150 | 1 | 1 | lump sum | 78.26%
CON-07 | MEP First Fix - L1-L3 | Construction | MEP Works | P3 | 2024-04-15 | 2024-05-10 | 2024-04-18 | 2024-05-15 | 2024-04-18 |  | 30% | Delayed | 5 | Sequenced after superstructure | Medium | 140000 | 45000 | 145000 | 2000 | 650 | 100 | 28 | risers installed | 86.15%
CON-08 | External Facade Installation - Phase 1 | Construction | Facade & Glazing | P3 | 2024-04-20 | 2024-05-20 | 2024-04-25 | 2024-05-28 |  |  | 10% | Delayed | 8 | Awaiting glazing package delivery | High | 180000 | 15000 | 190000 | 1600 | 120 | 60 | 5 | panels installed | 111.1%
CON-09 | Internal Partitions - L1 | Construction | Fit-Out & Finishes | P3 | 2024-04-22 | 2024-05-15 | 2024-04-22 | 2024-05-15 |  |  | 0% | Not Started | 0 | - | None | 70000 | 0 | 70000 | 800 | 0 | 900 | 0 | m2 partitions
OVH-01 | Site Overheads & Indirect Labor | Construction | Labor & Site Overheads | P3 | 2024-02-01 | 2024-04-30 | 2024-02-01 | 2024-04-30 | 2024-02-01 | 2024-04-30 | 100% | Completed | 0 | - | None | 150000 | 156800 | 162000
CNT-01 | Contingency Reserve | Construction | Contingency Reserve | P3 | 2024-02-01 | 2024-04-30 | 2024-02-01 | 2024-04-30 | 2024-02-01 | 2024-04-30 | 100% | Completed | 0 | - | None | 50000 | 6300 | 12000
CON-10 | Roofing & Waterproofing - Roof Level | Construction | Civil Works | P4 | 2024-05-05 | 2024-05-25 | 2024-05-08 | 2024-06-03 | 2024-05-08 |  | 40% | Delayed | 9 | Sequenced after superstructure topping out | Medium | 85000 | 30000 | 90000
CON-11 | External Hardscape & Paving | Construction | Landscaping & External Works | P4 | 2024-05-20 | 2024-06-10 | 2024-05-20 | 2024-06-10 |  |  | 0% | Not Started | 0 | - | None | 55000 | 0 | 55000

## Activities - Commissioning
Activity ID | Activity Name | Phase | Cost Category | Period | Baseline Start | Baseline Finish | Forecast Start | Forecast Finish | Actual Start | Actual Finish | % Complete | Status | Variance (Days) | Root Cause | Impact | Budget Cost (AED) | Actual Cost (AED) | Forecast Cost (AED) | Planned Hours | Actual Hours | Planned Output | Actual Output | Output Unit | Productivity Index
COM-01 | MEP Systems Testing & Balancing | Commissioning | Testing & Commissioning | P4 | 2024-05-10 | 2024-05-25 | 2024-05-12 | 2024-06-02 | 2024-05-12 |  | 20% | Delayed | 8 | Sequenced after MEP first fix completion | Medium | 60000 | 12000 | 62000 | 500 | 100 | 20 | 4 | systems tested | 100%
COM-02 | Fire Alarm & Life Safety Commissioning | Commissioning | Testing & Commissioning | P4 | 2024-05-20 | 2024-06-05 | 2024-05-20 | 2024-06-05 |  |  | 0% | Not Started | 0 | - | None | 35000 | 0 | 35000
COM-03 | Snagging & Defects Rectification | Commissioning | Snagging & Handover | P4 | 2024-05-25 | 2024-06-15 | 2024-05-28 | 2024-06-20 |  |  | 0% | Not Started | 5 | Follows facade and fit-out completion | Medium | 45000 | 0 | 48000
COM-04 | As-Built Documentation & O&M Manuals | Commissioning | Snagging & Handover | P4 | 2024-06-01 | 2024-06-15 | 2024-06-01 | 2024-06-15 |  |  | 0% | Not Started | 0 | - | None | 20000 | 0 | 20000
COM-05 | Client Handover & Training | Commissioning | Snagging & Handover | P4 | 2024-06-16 | 2024-06-20 | 2024-06-16 | 2024-06-20 |  |  | 0% | Not Started | 0 | - | None | 15000 | 0 | 15000

## Schedule Intelligence
Activity ID | Activity Name | Phase | Status | Variance (Days) | Root Cause | Impact
ENG-02 | Architectural Drawings - IFC | Engineering | Delayed | 6 | Client review delays | Low
ENG-03 | Structural Design & Calculations | Engineering | Delayed | 3 | Late input from geotech report | Medium
ENG-04 | MEP Coordination Drawings | Engineering | Delayed | 5 | Design clashes requiring rework | Medium
ENG-06 | Fire & Life Safety Design | Engineering | Delayed | 4 | Code compliance revisions | Low
ENG-08 | BIM Coordination Model - Final | Engineering | Delayed | 5 | Additional clash detection rounds | Low
PRC-02 | Ready-Mix Concrete Supplier Contract | Procurement | Delayed | 6 | Supplier price renegotiation | Medium
PRC-03 | Structural Steel Procurement | Procurement | Delayed | 10 | Mill lead-time longer than quoted | High
PRC-04 | MEP Equipment Long-Lead Items | Procurement | Delayed | 32 | Chiller delivery delayed by manufacturer | High
PRC-05 | Elevator & Lift Package | Procurement | Delayed | 10 | OEM factory backlog | Medium
PRC-06 | Facade & Glazing Package | Procurement | Delayed | 15 | Custom glass unit lead time | High
PRC-07 | Interior Finishes Materials Package | Procurement | Delayed | 7 | Tile supplier backorder | Medium
PRC-08 | Landscaping Materials & Plants | Procurement | Not Started | 0 | - | None
CON-01 | Excavation & Shoring | Construction | Delayed | 5 | Groundwater management | Medium
CON-02 | Foundation & Raft Slab Pour | Construction | Delayed | 8 | Rebar procurement delay upstream | High
CON-03 | Substructure Waterproofing | Construction | Delayed | 23 | Follows foundation pour completion | Medium
CON-04 | Superstructure - Ground to L3 Columns | Construction | Delayed | 7 | Concrete supplier renegotiation impact | High
CON-05 | Superstructure - Slab L1 | Construction | Delayed | 5 | Sequenced after column pours | Medium
CON-07 | MEP First Fix - L1-L3 | Construction | Delayed | 5 | Sequenced after superstructure | Medium
CON-08 | External Facade Installation - Phase 1 | Construction | Delayed | 8 | Awaiting glazing package delivery | High
CON-09 | Internal Partitions - L1 | Construction | Not Started | 0 | - | None
CON-10 | Roofing & Waterproofing - Roof Level | Construction | Delayed | 9 | Sequenced after superstructure topping out | Medium
CON-11 | External Hardscape & Paving | Construction | Not Started | 0 | - | None
COM-01 | MEP Systems Testing & Balancing | Commissioning | Delayed | 8 | Sequenced after MEP first fix completion | Medium
COM-02 | Fire Alarm & Life Safety Commissioning | Commissioning | Not Started | 0 | - | None
COM-03 | Snagging & Defects Rectification | Commissioning | Not Started | 5 | Follows facade and fit-out completion | Medium
COM-04 | As-Built Documentation & O&M Manuals | Commissioning | Not Started | 0 | - | None
COM-05 | Client Handover & Training | Commissioning | Not Started | 0 | - | None

## Cost Intelligence
Cost Category | P1 (AED) | P2 (AED) | P3 (AED) | P4 (AED) | Fcst (AED) | Variance vs Budget | % of Budget
Civil Works | 0 | 213000 | 189500 | 30000 | 505000 | 40000 | 108.6%
Material Procurement | 0 | 223000 | 75000 | 0 | 305000 | -5000 | 98.39%
Equipment Idle Time | 41200 | 0 | 0 | 0 | 46000 | 21000 | 184%
MEP Works | 0 | 187500 | 45000 | 0 | 335000 | 5000 | 101.5%
Labor & Site Overheads | 0 | 0 | 156800 | 0 | 162000 | 12000 | 108%
Engineering & Design Fees | 82000 | 96000 | 0 | 0 | 178000 | 3000 | 101.7%
Contingency Reserve | 0 | 0 | 6300 | 0 | 12000 | -38000 | 24%
Vertical Transportation | 0 | 180000 | 0 | 0 | 225000 | 5000 | 102.3%
Facade & Glazing | 0 | 0 | 155000 | 0 | 460000 | 20000 | 104.5%
Fit-Out & Finishes | 0 | 0 | 58000 | 0 | 168000 | 3000 | 101.8%
Testing & Commissioning | 0 | 0 | 0 | 12000 | 97000 | 2000 | 102.1%
Snagging & Handover | 0 | 0 | 0 | 0 | 83000 | 3000 | 103.8%
Landscaping & External Works | 0 | 0 | 0 | 0 | 95000 | 0 | 100%

## Productivity Intelligence
Activity ID | Activity Name | Phase | Planned Hours | Actual Hours | Hours Variance | Planned Output | Actual Output | Output Unit | Productivity Index | Rating
CON-01 | Excavation & Shoring | Construction | 4200 | 4850 | 650 | 620 | 540 | m3 poured | 0.75424 | Below Target
CON-02 | Foundation & Raft Slab Pour | Construction | 3100 | 3400 | 300 | 85 | 76 | tons fixed | 0.81522 | Below Target
CON-03 | Substructure Waterproofing | Construction | 1800 | 1650 | -150 | 40 | 34 | tons erected | 0.92727 | Below Target
CON-04 | Superstructure - Ground to L3 Columns | Construction | 2600 | 2900 | 300 | 310 | 275 | linear meters | 0.79533 | Below Target
CON-05 | Superstructure - Slab L1 | Construction | 1500 | 1400 | -100 | 210 | 205 | m2 completed | 1.0459 | On Target
CON-06 | Site Mobilization & Hoarding | Construction | 900 | 1150 | 250 | 1 | 1 | lump sum | 0.78261 | Below Target
CON-07 | MEP First Fix - L1-L3 | Construction | 2000 | 650 | -1350 | 100 | 28 | risers installed | 0.86154 | Below Target
CON-08 | External Facade Installation - Phase 1 | Construction | 1600 | 120 | -1480 | 60 | 5 | panels installed | 1.1111 | On Target
CON-09 | Internal Partitions - L1 | Construction | 800 | 0 | -800 | 900 | 0 | m2 partitions |  | No Data
COM-01 | MEP Systems Testing & Balancing | Commissioning | 500 | 100 | -400 | 20 | 4 | systems tested | 1 | On Target